## Android
Q2 New Scripts Plan - Reliant Mobile iOS
Weeks | 2023-04-08 | 2023-04-15 | 2023-04-22 | 2023-04-29 | 2023-05-06 | 2023-05-13 | 2023-05-20 | 2023-05-27 | 2023-06-03 | 2023-06-10 | 2023-06-17 | 2023-06-24 | 2023-07-01
Modules | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W14
Validating Multiple Accounts and Messages | 2023-04-08: 1; 2023-04-15: 1; 2023-07-01: 1. Completed Scripts Sign off. 2. Bulk run and Failure Analysis
Validation of fields in Login and Contact Information | bar: 2023-04-22 to 2023-04-29
Validating Bank Account and Credit Card screens | bar: 2023-05-06 to 2023-06-03
Validating Bill Screen Enhancement and Other scenarios in Bill screen | bar: 2023-06-10 to 2023-06-24
Grand Total | bar: 2023-04-08 to 2023-06-24
Q2 New Scripts Plan- Reliant Mobile Android
Weeks | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01
Modules | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W14
Payments | 2024-01-22: 1; 2024-01-29: 1; 2024-02-05: 1; 2024-02-12: 1; 2024-04-01: 1. Completed Scripts Sign off. 2. Bulk run and Failure Analysis
Deffered payments | bar: 2024-02-19
DOD | bar: 2024-02-26 to 2024-03-04
payment extention and Donate | bar: 2024-03-18
Registration | bar: 2024-03-11 to 2024-03-25
Grand Total | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Assumptions:
1. Automation environment is stable till the project is completed
2. Test data will be provided prior to the scripting is started for the test case
3. Any new implementation in the development code will not affect the completed automated scripts properties
4. No access issue and blockers for scripting

## Reliant
Q1 New Scripts Plan - Reliant Mobile iOS
Weeks | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-04 | 2023-03-11 | 2023-03-18 | 2023-03-25 | 2023-04-01
Modules | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W14
Payments | 2023-01-08: 1; 2023-01-15: 1; 2023-04-01: 1. Completed Scripts Sign off. 2. Bulk run and Failure Analysis
DoD | bar: 2023-01-08 to 2023-01-29
Registration | bar: 2023-02-05 to 2023-03-04
EV | bar: 2023-03-11 to 2023-03-25
Grand Total | bar: 2023-01-08 to 2023-03-25
Q1 New Scripts Plan- Reliant Mobile Android
Weeks | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01
Modules | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W14
Payments | 2024-01-22: 1; 2024-01-29: 1; 2024-02-05: 1; 2024-02-12: 1; 2024-04-01: 1. Completed Scripts Sign off. 2. Bulk run and Failure Analysis
DOD | bar: 2024-02-19
Registration | bar: 2024-02-26 to 2024-03-11
Deffered payments and payment extention | bar: 2024-03-18 to 2024-03-25
Grand Total | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Assumptions:
1. Automation environment is stable till the project is completed
2. Test data will be provided prior to the scripting is started for the test case
3. Any new implementation in the development code will not affect the completed automated scripts properties
4. No access issue and blockers for scripting